## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
Child Adoption Portal |  | 1 Month | 26/08/2021 | 26/09/2021 | 29/09/2021
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 26/08/2021 | 28/08/2021 | 3Days
1.2 | Finish webpage | 29/08/2021 | 2021-02-09 | 5Days
1.3 | Project Design | 2021-03-09 | 2021-03-09 | 1Days
2 | Coding
2.1 | Phase 1 | 2021-04-09 | 2021-10-09 | 7Days
2.2 | Phase 2 | 15/09/2021 | 21/09/2021 | 7Days
2.3 | Additional Features | 22/09/2021 | 25/09/2021 | 4Days
3 | Testing
3.1 | Phase 1 Testing | 2021-11-09 | 2021-12-09 | 2Days
3.2 | Modification /Any changes | 13/09/2021 | 14/09/2021 | 2Days
3.3 | Phase 2 Testing | 21/09/2021 | 22/09/2021 | 2Days
3.4 | Modification /Any changes | 22/09/2021 | 24/09/2021 | 3Days
3.5 | Final Testing | 25/09/2021 | 26/09/2021 | 2Days
4 | Documentation
4.1 | User Guide | 21/09/2021 | 23/09/2021 | 3Days
4.2 | Presentation | 25/09/2021 | 26/09/2021 | 2Days

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Team Lead
| Member Name | Neha Katekar
| PRN No | 201543181053
| Description | Front-End, ERD
2 | Role | Group Member
| Member Name | Pranita Deshpande
| PRN No | 201543181021
| Description | Front-End, Use-Case
3 | Role | Group Member
| Member Name | Komal Jagtap
| PRN No | 201543181032
| Description | Back-End, DataBase
4 | Role | Group Member
| Member Name | Shikha Singh
| PRN No | 201543181098
| Description | Back-End,Use-Case